## Slide 1
RO19 "Public Health Initiatives" Romania
Ministry of Health which aims to "improve public health and reduce health inequalities".
Romania receive financial assistance through Norway Grants 2009-2014

## Slide 2
The Program Value is 26,592,941 euro, from which: - 85% Norway Grants - 22,603,999.85 Euro - 15% Ministry of Health co-financing - 3,988,941.15 Euro
The implementation period is
16 of January 2014 – 30 of December 2017
The expected outcomes of the Programme are: - Improved prevention and treatment of communicable diseases (including HIV/AIDS and TB); - Developed resources for all levels of health care; - Life-style-related diseases prevented or reduced.

## Slide 3
The programme contains, 8 predefined projects, as follow: - RO 19.01 Improving the health status of the Romanian population in Romania by increasing Tuberculosis control (budget: 10,748,280 Euro); - RO 19.02 Strengthening the prevention and control of HIV/AIDS, HVB, HVC in Romania (budget: 1,373,470 Euro); - RO 19.03 Strengthening the National Network of Roma Health Mediators to Improve the Health Status of Roma Population (budget: 1,052,910 Euro); - RO 19.04 Multi-level interventions for prevention of lifestyle related non communicable diseases (NCD) in Romania (budget: 1,115,120 Euro);

## Slide 4
- RO 19.05 “Better patient outreach and services planning through better Diseases Registries”(budget 1,035,000 Euro); - RO 19.06 “Increase Capacity of the Romanian Health Sector to Implement Organized Screening for Cancers Amenable To Cost-Effective Early Detection Interventions” (budget 1,500,000 Euro); - RO 19.10 “Improved healthcare for high-risk pregnancy, premature birth and haematological diseases” (budget 1,760,362 Euro); - RO 19.11 “Improving pediatric oncology and hematology services in Romania through the acquisition of goods, services and specialized works” (5,655,653 Euro).

## Slide 5
Status 31st of October 2015
The amount used until 31 of October 2015 within the programme and predefined projects is 6,986,274.68 Euro, representing 26,27% from total value of the Programme.

## Slide 6
Pre-defined project RO 19.01
„Improving the health status of the Romanian population in Romania by increasing Tuberculosis control”
Project promoter:
The Institute of Pneumology "Prof. Dr. Marius Nasta"
Project partners: Romanian Angel Appeal Fundation (partner consortiun leader) şi Center for Health Policies and Services (CPSS).
Norwegian partner: LHL International Tuberculosis Foundation
Budget: 10 748 280 euro
Until 31st of October 2015, the project is 43% completed.
For additional information please visit
http://control-tb.marius-nasta.ro/

## Slide 7
Main achievements until 31st of October 2015:
9498 patients tested for TB by rapid methods, from which 2297 found with sensitive TB and 514 with MDR-TB;
289 patients with MDR-TB receive full course treatment;
423 staff of TB network countrywide were trained in drug management, TB infection control and surveillance;
4 training sessions with the purpose of building capacity for the NTP Central Coordination Unit ( The National Program for Tuberculosis Control ) were organized;
the national electronic TB database is currently under upgrading;
the project information and results were disseminated to 300 stakeholders;
8 laboratories were already equipped with equipment for TB rapid testing;
540 TB patients received incentives in order to maintain treatment adherence and to avoid treatment interruptions;
1 press conference organized

## Slide 8
Pre-defined project RO 19.02
„Strengthening the prevention and control of HIV/AIDS, HVB, HVC in Romania”
Project Promoter: National Institute of Infectious Diseases “Prof. Dr. Matei Bals” Bucharest
Project Partners: NGO consortium of ARAS Romanian Association against AIDS, RHRN - Romanian Harm Reduction Network, ALIAT - Alliance for the Fight against Alcoholism and Drug Abuse and Parada Foundation.
Budget: 1.373.470 Euro
Until 31st of October 2015, the project is 80% completed.
For additional information please visit:
http://www.mateibals.ro/ and http://www.h-alert.ro/

## Slide 9
Main achievements until 31st of October 2015
8392 information sessions were conducted to reduce the harm of drug use;
723 HIV tests were made for intravenous drug users;
204,705 condoms were distributed;
363010 disposable syringes were provided for intravenous drug users to reduce the risk of infection with HIV, HCV and HCV. There were recovered and incinerated 100,010 syringes.
20,157 tests for detecting infections of HIV, HBV, HCV in the general population with risk factors for chronic infections were conducted.
329 specialists were trained as trainers for other specialists involved in medical services offered to the general population and also risk populations.

## Slide 10
Pre-defined project RO 19.03
„Strengthening the National Network of Roma Health Mediators to Improve the Health Status of Roma Population”
Project Promotor: National Institute of Public Health
Project Partner: Roma Centre for Health Policies- SASTIPEN
Budget: 1.633.360 Euro
Until 31st of October 2015, the project is 60% achieved.
For additional information please visit
http://www.reteaua-amc.ro/

## Slide 11
Main achievements until 31st of October 2015:
45 community workers and 45 Roma mediators were hired within the project starting with May 2015;
45 community health centres functional, from which 43 where refurbished by the project and 2 by local authorities;
434 roma communities were selected by the project and benefiting from community health services;
118700 vulnerable people served by Roma health mediators and community workers;
1 study assessing the health needs of the Roma community was finalized;
50 professionals from the District Health Directorates trained as trainers in September 2015, the training of the Roma mediators (45 persons) was completed in 31st of October 2015;
the 45 communities workers were trained, and the 45 agreements with local authorities were signed;

## Slide 12
Pre-defined project RO 19.04
”Multi-level interventions for prevention of lifestyle related non communicable diseases (NCD) in Romania”
Project Promoter: National Institute of Public Health, Bucharest, Romania
Project partners:
Project partner 1: Targu-Mures University School of Medicine and Farmacy Medicine Faculty;
Project partner 2: ALIAT - Alliance for the Fight against Alcoholism and Drug Abuse;
Project partner 3: Romanian Health Psychology Association
Project partner 4: Foundation National Centre for Studies in Primary Care
Budget: 1.384.180 Euro
Until 31st of October 2015, the project is 75% achieved.
For additional information please visit http://insp.gov.ro

## Slide 13
Main achievements until 31st of October 2015:
Guidelines to prevention recommendations addressed major risk factors relating to lifestyle (diet, physical activity, alcohol) at primary health care level were elaborated and sent to validation by consensus;
Selection and ranking of information and resources for research made;
Started training sessions for prevention guidelines and implementing IT solutions in 100 offices MF;
TOT sessions on guidelines for intervention in schools and kindergartens were competed;
All descriptive statistical results for HBSC (Health Behavior in School Aged Children )/ 2015 study were completed;
The final national report HBSC Romania 2014/ 2015 were finalized;
There have begun talks on the workshop of consensus to implement clinical guidelines for prevention.

## Slide 14
Pre-defined project RO 19.05
”Better patient outreach and services planning through better Diseases Registries”
Project Promoter: National Institute of Public Health, Bucharest, Romania
Budget: 1,035,000 Euro
Until 31st of October 2015, the project is 57% completed.
For additional information please visit
https://insp.gov.ro

## Slide 15
Main achievements until 31st of October 2015:
5 assessment reports, one for each registry finalized;
over 70 meetings of the technical working groups;
5 methodologies for disease registries were elaborated;
launching conference organized;
1 press release;
5 drafts of Ministerial Order for disease registries elaborated.

## Slide 16
Pre-defined project RO 19.06
”Increase Capacity of the Romanian Health Sector to Implement Organized Screening for Cancers Amenable To Cost-Effective Early Detection Interventions”
Project Promoter: Institute for Oncology „Prof. Dr. Ion Chiricuţă”, Cluj-Napoca
Project partners: Project partner: Oslo Universitetssykehus HF / Kreftregisteret (Norwegian Partner)
Budget: 1.806.809 Euro
Until 31st of October 2015, the project is 52% completed.
For additional information please visit http://cedicrom.iocn.ro

## Slide 17
Main achievements until 31st of October 2015:
Feasibility study of screening for breast cancer is underway, the findings of which can be defined only at the completion of the project;
Guidelines and procedures for support / software implementation of two organized screening programs have been defined and are currently disseminated in the body of health professionals;
There were carried out 2203 PAP tests with app. 3,8% positive cases currently under management and 1,868 mammograms with dual reading and arbitration with about 10% positive cases undergoing supplementary investigations;
The mobile unit is functional and has made over 40 visits to Roma communities and other isolated / disadvantaged communities with the purpose of information and sampling tests;
It was held a press conference in October 2015 in the Roma community from Pata Rit (Cluj county) attended by Dr. Florian Nicula, Project Manager, and Ms. Trude Andreassen from Kreftregisteret, the Norwegian partner in the project.

## Slide 18
Pre-defined project RO 19.10
”Improved healthcare for high-risk pregnancy, premature birth and haematological diseases”
Project Promoter: University Emergency Hospital Bucharest - UEHB
Budget: 1.760.362 Euro
Until 31 of October 2015, the project is 60% achieved
For additional information please visit
http://1910.ro/index.php/acasa/

## Slide 19
Main achievements until 31 of October 2015
Renovation of the laboratories and care units was finalized;
75% equipment and reagents were purchased;
The investigations and therapeutic procedures in October 2015 are:
44 infants hospitalized in NICU and Premature Compartment, of which 7 hospitalized in the intensive care unit (TINN) and 4 preterm infants;
Referrals to other hospitals 1 case transferred to other hospital;
Gynecology: 370 patients enrolledin the program, 115 monitoring cardiotocographs, 11 colposcopy;
370 tests for each of the following analytes: antithrombin, protein C, factor V Leyden, protein S, lupus anticoagulant screening, confirmation lupus anticoagulant factor, homocysteine.
370 TORCH tests, each test include CMV IgG and IgM, IgG and IgM Rubella, Toxoplasma IgG and IgM;
9 markers by flow cytometry test per case;
1 training program for users SUUB (ultrasound gynecology department).

## Slide 20
Predefined project RO 19.11
“Improving pediatric oncology and hematology services in Romania through the acquisition of goods, services and specialized works”
Project promoter: “Prof. Dr. Al Trestioreanu” Institute of Oncology, Bucharest
Project partners:
Project partner 1 - "Louis Turcanu" Children's Emergency Hospital, Timisoara;
Project partner 2 – Oncologic Institute“Prof.Dr.I.Chiricuta” Cluj-Napoca;
Project partner 3 - ”Sf. Maria” Children's Emergency Hospital Iasi.
Budget: 5,655,653 Euro
Until 31st of October 2015, the project is 30% completed
For additional information please visit http://www.iob.ro

## Slide 21
Main expected results:
Acquiring a number of equipment items that will improve results obtained from the treatments tailored for the patients’ risk category with positive outcome on survival, namely:
  3 Nuclear magnetic resonance machines, 3 Remote monitoring system, 3 Anesthesia devices (Bucharest, Iasi, Cluj);
  A remote monitoring and anesthesia system for the radiotherapy device, a CT machine for treatment plan and a Portable EKG (Bucharest);
  Portable ultrasound (Timisoara);
  Criocylinder for liquid nitrogen supply and storage (Timisoara);
  Apparatus for dispensing plasma levels (Timisoara);
  An Osteodensitometer and a toxicological analyzer (Iasi);
Training a number of 289 specialists in order to improve the pediatric hematology and oncology activity of staff (physicians, medical assistants, nurses);
Developing a campaign of information, education and communication for pediatric oncology and hematology field

## Slide 22
Ministry of Health
http://www.initiativeinsanatate.ms.ro/